## Schedule template
Course Schedule Template
Course Name |  | Mastering Puppet for Large Infrastructures
Product ID |  | V05517
Course ISBN[13] |  | 2527OS
Preliminary Draft Video Schedule
Days For Each Section | Section Number | Section Name | Initial Delivery Date | Comments | START Date | No of Sections | No of days per section
2 |  | Sample Screencast | 2016-05-10 | You will be provided with 2 days from the start date of the project to draft the sample screencast and submit it to your editor | 2016-05-08 | 7 | 3
3 |  | Tentative timeline to finalize sample screencast | 2016-05-13 | You will receive feedback on the screencast within a day. This feedback needs to be worked on and you need to submit the revised draft to your editor and finalize it in the next 2 days.
5 | 1 | Section 1: Getting Started | 2016-05-18 | On acceptance of the sample, you need to start working on recording Section 1.
5 |  | Tentative timeline to finalize section 1 | 2016-05-23 | Our editor will help you iron out any major issues in the section of scripts, and provide you feedback in 3 days. You get 2 more days to finalize this section's script.
5 | 2 | Section 2: Architecting Puppet for scalability, redundancy and performance | 2016-05-23 | On submission of the Section 1 you need to start working on Section 2
5 |  | Tentative timeline to finalize section 2 | 2016-05-28 | Our editor will help you iron out any major issues in the section of scripts, and provide you feedback in 3 days. You get 2 more days to finalize this section's script.
5 | 3 | Section 3: Using PuppetDB | 2016-06-02 | You get 6 days to draft Section 2 once you submit Section 1. On submitting this section, start working on Section 3. You need not wait for the feedback to start drafting the next section.
5 | 4 | Section 4: Extending Puppet functionalities | 2016-06-07 | Starting section 3, you will have a feedback cycle of 3 days from the editor. The feedback can be worked upon and submitted along with the next section on the delivery date mentioned in the table.
5 | 5 | Section 5: Puppet reporting | 2016-06-12
5 | 6 | Section 6: Testing and Troubleshooting | 2016-06-17
5 | 7 | Section 7: Wrapping Up | 2016-06-22
2 | 8 | Course Overview | 2016-06-24
Technical Reviewing and Rewrites Stage - The content that has been editorially accepted by our editors will be reviewed by technical experts contacted by us. They would provide feedback to improve the quality of the course. This feedback would be shared with you and you would work on the Final Draft of the Videos. We expect the rewrite stage to take not more than 3 days per section listed above.
Final Draft Videos Schedule
Days For Each Section | Section Number | Section Name | Delivery Date | Comments | START Date
3 | 1 | Section 1: Getting Started | 2016-07-04 | Once the sample is accepted, you can start recording all the videos of the section. | 2016-07-01
3 |  | Section 1 Feedback | 2016-07-07 | Our editors will provide you with feedback within 3 days.
3 | 2 | Section 2: Architecting Puppet for scalability, redundancy and performance | 2016-07-10 | Start recording Section 2 once you submit Section 1 to your editor. During this time, you will have to submit the revised Section 1 if any changes were requested
3 | 3 | Section 3: Using PuppetDB | 2016-07-13 | Based on the feedback received, you are expected to deliver Section 3 videos, and section 2 revisions within 5 days.
3 | 4 | Section 4: Extending Puppet functionalities | 2016-07-16 | Section 3 onwards, we do not expect major revisions as you will be familiar with the requirements at this stage of the project.
3 | 5 | Section 5: Puppet reporting | 2016-07-19
3 | 6 | Section 6: Testing and Troubleshooting | 2016-07-22
3 | 7 | Section 7: Wrapping Up | 2016-07-25
2 |  | Course overview | 2016-07-27
Formulas:
Initial Delivery Date = SUM([START Date]+[Days For Each Section])
Initial Delivery Date = [Initial Delivery Date, row above]+[Days For Each Section]